## Hoja1
Item number | Action Item Description from the Minutes | Responsible Party | Target Completion Date | Priority | Status / Comments
22.04.01 | Go to tender and get quotes for signposts and report back at the next Board Meeting | HRGR Admin | 10.6.22 |  | Alma Rotulación has been contacted - working on the design to send to the company
22.04.02 | Draft an email with the information about the proposal on the fire alarm (cost 300€) | Richard Deeley | 15.5.22 |  | This action closed - report given to the PPs 12 May 22 with request to send to their BPs. However, further action to be determined at BM 10.6.22 - Board will inform on how many BPs have replied and agreed with it 10.6.22 - Answers from PPs in a week today.
22.04.03 | Provide the information produced by RD about fire alarm to the BPs in each phase | PPs | 10.6.22 |  | Following consultation with BPs, implementaion needs to be confirmed by the PPs for each of the buildings in their phase.
22.04.04 | Guidance about what is practical to discuss during board meetings will be provided to each PP | RP, PPs & Pepa | As and when required |  | Ongoing - 10.6.22: It is better to generate more discussions prior to the Board meeting. The disadvange is that it also generates a big traffic of emails that is exactly what we are trying to avoid.
22.04.05 | Some items that are raised by owners/BP to PPs may be better to circulate in advanced of the Board Meeting via email, to speed up the response and reduce debating time at the BM. | RP & PPs | N/A |  | Closed - PPs to implement as deemed necessary.
22.04.06 | Communications to BPs - A template is available for anyone that wants one. | RP & PPs | 15.5.22 |  | Closed - template sent by RP to the PPs. PPs to alter as they consider necessary and send to their BPs
22.04.07 | Instruction course for new and current PB´s advising of roles and responsibilities | Richard Deeley | 31.5.22 |  | RD already has done the trial of the course with 3 BPs so the date for the official training day (on a Saturday morning) will be set up shortly. 10.6.22: the training course was done the 28.05.2022. The date for the instructions course of the Spanish speaking BP and for the second one of the English speaking BPs will be provided shortly.
22.04.08 | Investigate the options for use of Microsoft 365 Outlook for current PP emails accounts | Pepa | 15.5.22 |  | 10.6.22 work in progress
22.04.09 | Microsoft 365 SharePoint - Training required for PPs. | Pepa | 31.5.22 |  | Some of the PPs have already had access to the SharePoint and had been able to check docs, etc. For those that still are having problems, it will be check when they are on site. 10.6.22 work in progress
22.04.10 | Information centre _ Get quotes for the necessary actions in the IC to improve it | HRGR Admin | 31.5.22 |  | Ask Manuel if we can get a long term rental of the proshop to allocate the information office. 10.6.2022
22.04.11 | Training for the volunteers helping in the IC | TBD | TBD |  | Work in progress 10.6.2022
22.04.12 | Surgery from the PPs - Draw a rota of when PPs are on the Resort | Patrick Flynn | 10.6.22 |  | Various PPs have provided comment after the BM and the proposal will be further reviewed at the next Board Meeting for a final decision. 10.6.2022: It is going to be trialed by 3 BM (GH,PF&SB) - upstairs on El Casón - They will decide how to manage it. Early July. Only Phases 6 & 7 to start with.
22.04.13 | Look for an alternative professional Spanish company to upgrade the webpage. Patrick Flynn agreed to contact a company he recommends with English management but based in Spain. | Patrick Flynn | 15.5.22 |  | Richard & Shaneen had a zoom meeting with the Spanish web designer the w/c 9.5.22. The designer is working on a proposal that Patrick will present to the Board on 10.6.22. Patrick is having a meeting with Tim Bailey of Impact Creative who are the current web page hosts; Patrick will report back to the Board anything he discusses with Tim.
22.04.14 | Shaneen Benson to carry out a handover of the webpage with John Barr | Shaneen Benson | 10.06.22 |  | Item included in the Agenda of the BM 10.6.22
22.04.15 | Monthly newsletter - RP to approach Julie Osman to help produce it so it is more interactive with other information areas | Richard Deeley | 10.6.22 |  | In progress 10.6.22
22.04.16 | Owners Information pack - send the final version in English to the Board for their review in case they wish to add or update something. | HRGR Admin | 10.6.22 |  | In progress 10.6.22
22.04.17 | Owners information pack - do a general communicaton to all the owners and use for the new owners | HRGR Admin | 10.6.22 |  | In progress 10.6.22
22.04.18 | Animal Protection and Welfare Code - the docs produced by John Barr will be shared with the Board to decide what to do | RP & PPs | 15.5.22 |  | Closed - the proposed comms were sent to the Board by RD. After an exchange of opinions it was agreed not to send them out
22.04.19 | Procurement Policy - Write a revised version | Bernard Loughrey & Nigel Smith | 10.6.22 |  | 10.6.22 First draft of Procfurement Policy & Procedure prepared; Nigel will review after he returns to UK tomorrow.
22.04.20 | Health & Safety legal requirements - Ask the lawyer to clarify which H&S legal docs are required to manage the Resort | Pepa | 10.6.22 |  | 10.6.2022 As a community we are not subject to it. However, it is better to have it. Community of owners are not obliged to this kind of policies so the action will be remove the current one from 2009.
22.04.21 | STV contract - agreed to initiate a weekly / monthly review process from 1st May 2022 | Richard Deeley, Viv Church & Pepa | From 1.05.2022 |  | Closed - VCh -to attend weekly meeting; and RD, VCh & Pepa to attend monthly meeting. 10.6.22: the priority now is the irrigation.
22.04.22 | Safety datasheets - requested from STV | Richard Deeley | 10.6.22 |  | The datasheets were sent by STV and RD will provide feedback at the next BM. 10.6.22: all the products used are approved by the corresponding gouverment
22.04.23 | Weekly gardening tasks - STV will provide with this info every Thursday morning for the following week | Viv Church & Pepa | Weekly |  | Closed - action implemented and ongoing
22.04.24 | Surveys - Upgrade the 2022 surveys to adapt to the current situation | Richard Deeley | 31.12.22 |  | RD will be running the surveys in 2022
22.04.25 | Urbit App - Speak to Jose (maintenance man) to request that a comment is added every time he closes an incident on the App | Pepa | 2022-05-01 |  | Closed
22.04.26 | Urbit - a relaunch is required and attempt made to explore what other devices Urbit can be accessed, e.g. laptop | Wendy Walker | 10.6.22 |  | 10.06.2022 - Work in progress
22.04.27 | Urbit - response times by all parties will be measured to ensure that incidents are resolved in a timely manner | Wendy Walker & HRGR Admin | N/A - Ongoing |  | Ongoing
22.04.28 | D&O insurance - send an explanation of what is included and covered by the D&O policy | Pepa | 10.6.22 |  | 10.06.2022 - Work on process
22.04.29 | Contacts - Produce a document to be laminated and posted in the buildings. It will show the policy number, contact details, details of the excess amount, and other details for different communal services | Gordon Hutchinson | 10.6.22 |  | Viv Church will help with the lamination once the final document is ready. Work in progress 10.06.22
22.04.30 | Information to BPs - the lift inspections / repairs will be sent on a monthly basis | HRGR Admin | From 1.06.2022 |  | 10.06.22 work in process
22.04.31 | Planning Permissions - the Board requires advice from the Lawyer to clarify the correct implementation of owners proposals with respect to approval from Murcia Town Hall and HRGR planning approval. | HRGR Admin | 10.6.22 |  | Item included in the Agenda of the BM 10.6.22
22.04.32 | Traffic Calming - approved in 2021 to purchase 2 signs to measure the speed | Gordon Hutchinson | 10.6.22 |  | GH is in the process of purchasing them. 10.06.2022 work in progress - getting quotes
22.04.33 | Pools usage - to finalise the report and get it circulated to the Board. The Board will review the report and decide on the way forward | Shaneen Benson | 6.5.22 |  | Report issued - update/review to be undertaken at the next BM 10.06.2022
22.04.34 | Extra guard for the summer - Define the duties of the security guard and confirm the period the staff will be covering in summer. Also get the cost for the corresponding period. | TBD | Before 1st July |  | Item included in the Agenda of the BM 10.6.22
22.04.35 | Maintenance & repairs - arrange the services of 1 or 2 builders to get repairs completed quicker | Gordon Hutchinson & HRGR Admin | TBD |  | Item included in the Agenda of the BM 10.6.22
22.04.36 | Garage water ingress - RP to produce a comm to PPs regarding this item and then PPs to send to their phase BPs | Richard Deeley | 31.5.22 |  | Communication issued to PPs; PPs to confirm onward issue to BPs 10.06.2022 many BPs have contacted Terasprom to check their garages and give quotes to correct the water ingress.
22.04.37 | Landscaping Q&A - Board to give the final approval | Pepa | 31.5.22 |  | Sent and closed
22.04.38 | Open Forum Q&A - Board to give the final approval | Pepa | 15.6.22 |  | Work in progress
22.04.39 | Survey results - Board to provide final approval | Richard Deeley & Pepa | 30.6.22 |  | Work in progress
22.04.40 | Picnic area - get quotes to brick up at the roadside to prevent any access | HRGR Admin | 10.6.22 |  | The area has been reviewed and due to the design of the stairs to access the picnic area a new wall at the front of the stairs is not going to avoid people accessing or teenagers jumping over the wall. Therefore, Charlotte has requested quotes to fit a fence to cover the front and side facing the road. 27.5.22: 3 quotes have been received for 3 different options of closing the access to the area
22.04.41 | Security guard - Buy a gift for his retirement | Gordon Hutchinson | 10.06.2022 |  | When is his last day in HR? Ask John Frizell for further details and decide who is going to buy the Scottish whisky. 10.06.2022 The guard Antonio was invited to the office so he could receive his retirement gift. He was very greatful for all the time he has spent working in HR and for how nice the owners have always been with him.
22.04.42 | Bank in Phase 7 - Erosion at the bottom of Phase 7 close to the wall of Peraleja is undermining one of the perimeter lamp posts. Arrange for investigation to be done to determine the necessary actions to mitigate the risk of collapse of the post. | HRGR Admin | 10.6.22 |  | Pepa has contacted a contractor dealing with civil works and expect to have a visit to the area shortly. 10.06.2022 the street lamp has been moved to the new location. Cerrado
22.04.43 | Bank in Phase 7 - Once the picnic area is permanently closed, any remaining funds will be held for the bank. However, no money will be spent until a visit and report is provided by Murcia Town Hall | HRGR Admin | 10.6.22 - update at BM |  | Pepa will be contacting the Town Hall of Murcia to find out the procedure to get a visit and a report from MTH 10.06.2022 work in progress
22.04.44 | Distribution Whatsapp list - a list has been created for the PPs for urgent and inmediate issuess. The same has been done with the BPs for whom we have mobile numbers. It does not breach any Data Protection regulation. An email is to be sent to the BPs so those who are interested and have not been included in the list yet, can contact HRGR Admin and request to be included. | HRGR Admin | 31.5.22 |  | Closed
22.04.45 | Sharing phone numbers - PPs to send an email with the authorization to share their phone numbers with the other PPs for informal communications | PPs | 31.5.22 |  | 10.06.2022 work in progress - an email needs to be sent to Pepa with the PPs authorization. Done and Closed
22.04.46 | El Casón - evaluation of the options to purchase el Casón | Gordon Hutchinson and Patrick Flynn | 31.5.22 |  | There was a meeting with the lawyer of the community on 17.05.2022. An update can be given at the next BM on 10.06.22 - The meeting with Manuel took place. It is now for Manuel to discuss with PwC whether they are open to an offer. The Community is not a possible purchaser. It can be approached by a different body.
22.04.47 | PW garage spaces - Get a report in detail to present to the BPs and owners about the options and associated costs | Pepa Pérez | 31.7.22 |  | Pepa is working with the lawyer of the community to get all the details for the report. It is not possible to know yet when the information will be available. This item was also commented at the meeting with the lawyer on 17.05.2022. An update can be given at the next BM on 10.06.22 - work on progress
22.04.48 | Contract for the Administrator - expedite the lawyer to finalise the contract. | Richard Deeley | 31.5.22 |  | Closed